## TestCase
Product Nane | Bikroy | TC Execution Start Date | 2024-01-05
Module Name | Core Functionalities | TC Execution End Date | 2024-04-05 | [5 empty] | PASS
Test Case Planning & Executed By | Saima Binta Younus | [7 empty] | Out of Scope
TOTAL
Test Scenario | Test Case ID | Title/Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status
Registration/SignUp | SignUp_01 | Verifying SignUp with valid phone number | User should able to SignUp | Successful Login with valid credentials | "01655527092" | 1. Goto Bikroy.com 2. Click on Login 3. Try to login with valid phone number |  |  | Passed
| SignUp_02 | Verifying Login with Invalid OTP | User should not able to SignUp | Found as per expectation | 349878, 01928, 7383737382 | 1. Goto Bikroy.com 2. Click on Login 3. Try to login with valid phone number 4. Input invalid otp |  |  | Passed
| SignUp_03 | Verifying SignUp with Invalid phone number | User Should not able to SignUp | Found as per requirement | "0000004834758475", "7564786878465845", "0000000000" | 1. Goto Bikroy.com 2. Click on Login 3. Try to login with invalid phone number |  |  | Passed
| SignUp_04 | Verifying SignUp using Facebook | User should able to SignUp | Found as per requirement | Valid username and password : "Saima Nova" "nahdgrtrijsje34" | 1. Goto Bikroy.com 2. Click on Login 3. Try to login with facebook credentials |  |  | Passed
| SignUp_05 | Verifying SignUp using valid Google account | User should able to SignUp | Found as per expectation | Valid google account | 1. Goto Bikroy.com 2. Click on Login button 3.Try to SignUp using google account |  |  | Passed
| SignUp_06 | Verifying SignUp using valid Email | User should able to SignUp | Found as per expectation | Valid email "saima@gmail.com" | 1. Goto Bikroy.com 2. Click on Login button 3. Check alignment of signup page |  |  | Passed
| SignUp_07 | Verifying SignUp using invalid email | User should not able to SignUp | Found as per expectation | "1234@gamil.com", "@gmail.com", "str56.com" | 1. Goto Bikroy.com 2. Click on Login 3. Try to Signup with invalid email |  |  | Passed
| SignUp_08 | Verifying SignUp with email credential fileds | User will be able to SignUp with only valid details | User is able to SignUp with invalid credentialds | name : 123 ,email : saimabintayounus1999@gmail.com, password : 12345 ,confirm password : 12345 | 1. Goto Bikroy.com 2. Click on Login 3. Try to login with email credentials 4. Input invalid data for each field 5. Check the SignUp status | Bug Screenshot |  | Failed
| SignUp_09 | Verifying Password Strength while SignUp with email | A guildline to input strong password | Not Found as per expectation | password : 12345 confirm password : 12345 | 1. Goto Bikroy.com 2. Click on Login 3. Try to login with email credentials 4. Input weak data for password field 5. Check the SignUp status | Bug Screenshot |  | Failed
Searching Items | Searching_01 | Verifying the search results are accurate and up-to-date. | Users are able to see up-to-date products | Found as per expectations | "saree", "mobile phone", "laptop" | 1. Goto Bikroy.com 2. Click on Login 3. Click on create an account 4. Search any product on search bar |  |  | Passed
| Searching_02 | Verifying advance search filters | Users are able to utilize advanced search filters such as price range, location, condition, etc | Working as per expectation | location : "dhaka", sort : "high to low" ,"category : mobile phone" | 1. Goto Bikroy 2. Click on Login 3. Click on create an account 4. Search on search bar 4. Search with advance flters |  |  | Passed
| Searching_03 | Verifying empty search | System should prompts the user to enter a search keyword | System returning with all categories of commercial advertisements | " " | 1. Goto Bikroy 2. Click on Login 3. Click on create an account 4. Search on search bar with empty fields | Bug Screenshot |  | Failed
| Searching_04 | Verifing search suggestions/autocomplete | System shows search suggestions of partial keywords | Found as per expectations | "mob" , "lap" | 1. Goto Bikroy 2. Search on search bar with partial keyword |  |  | Passed
| Searching_05 | Verifying search bar with invalid search keys | System should suggests users for valid Input | System returning with invalid search output | "01", "12", "45" | 1. Goto Bikroy 2. Search on search bar with invalid keywords | Bug Screenshot |  | Failed
| Searching_06 | Verifying Search results details | System will apppear all relevant information about the searches | Found as per expectation | "Desktop" | 1. Goto Bikroy 2. Search on search bar 3. Check Search details appear in the system |  |  | Passed
| Searching_07 | Verifying Related Searches | System should show related searches or recommended listings. | No previous related searches or recommendations |  | 1. Goto Bikroy 2. Check if any recommendations or arrives related to previous searches |  |  | Failed
| Searching_08 | Verifying user recent searches | User should able to see recent searches | System is not showing any recent searches | N/A | 1. Goto Bikroy 2. Check if any recent searches appears | Bug Screenshot |  | Failed
Blank
Browsing | Browsing_01 | Verifying basic page navigation | Homepage loads correctly when the website is accessed | Homepage Loads correctly |  | 1. Goto Bikroy.com 2. Check homepage loading |  |  | Passed
| Browsing_02 | Verifying browsing by category | System will appear by category | Found as per expectation | "mobile", "laptop" | 1. Goto Bikroy.com 2. Search any Item by category 3. Verify items appear by category |  |  | Passed
| Browsing_03 | Verifying pagination | System will show test pagination functionality for browsing through multiple pages of search results | Found as per expectation | "Table Lamp" | 1. Goto Bikroy.com 2.Search for any item 3. Examine search result 4. Check If the results are synchronized with latest result in multiple pages |  |  | Passed
| Browsing_04 | Verifying Bookmarking Products | Test the functionality to bookmark or save products for later viewing. | Found as per expectation | "lamp" | 1. Goto Bikroy.com 2.Search for any item 3. Find the expected item 4. Save the Item for later |  |  | Passed
| Browsing_05 | Verifying recently viewed items for logged-in users | System will store recently viewd items | System is not storing any data from previous search | "Pen" | 1. Goto Bikroy.com 2.Search for any item 3. check if any previous items shows |  |  | Failed
| Browsing_06 | Verifying Cross-Browser Compatibility | Working on different web browsers (Chrome, Firefox, Safari, Edge) | Found as per expectation |  | 1. Goto Bikroy.com from different browsers 2. Check the browser compatibility |  |  | Passed
| Browsing_07 | Verifying responsiveness on different devices | Working on different device without any trouble | Found as per expectation |  | 1. Goto Bikroy.com from different devices 2. Check the responsiveness of the system |  |  | Passed
Blank
Purchasing Item | Purchase_01 | Verifying Add to Cart Functionality | Users can add items to their cart from the product listing page | No Add to Cart Options |  | 1. Goto Bikroy.com 2. Search any item 3. Add desired item 4. check the item is added to the cart |  |  | Failed
| Purchase_02 | Verifying Order Summary | System will show a Order summary before purchase | No Purchase Options |  | 1. Goto Bikroy.com 2. Search any item 3. Add desired item 4. check the item is added to the cart 5. Proceed to Purchase the Item |  |  | Failed
| Purchase_03 | Verifying Order Tracking | System will show a status on the product | No Options for tracking |  | 1. Goto Bikroy.com 2. Search any item 3. Add desired item 4. Proceed to durther steps |  |  | Failed
| Purchase_04 | Verifying Order Modification or Cancellation | System has the ability to modify or cancel an order before it is shipped. | No Options related to this field |  | 1. Goto Bikroy.com 2. Search any item 3. Add desired item 4. Proceed to durther steps |  |  | Failed
| Purchase_05 | Verifying Order Completion and Delivery | System will make sure of completion of the order and delivery of purchased items | No Options related to this field |  | 1. Goto Bikroy.com 2. Search any item 3. Add desired item 4. Proceed to durther steps |  |  | Failed
Blank
Blank
User Account Management | User Management_01 | Verifying Login Functionality | User will be able to login with valid credentials | Found as per expectation |  | 1. Go to Bikroy.com 2. Try to login with valid credentials |  |  | Passed
| User Management_01 | Verifying Forgot Password functionality | Users receive a password reset link and can set a new password | Found as per expectation | username: "Saima Nova" password: " " | 1. Go to Bikroy.com 2. Try to login with valid credentials without password filed 3. Click on forget password option 4. Check the password resent link |  |  | Passed
| User Management_03 | Verifying reset security of user account | User is able to update account security | No option for account security |  | 1. Go to Bikroy.com 2. Login to the account 3. Goto account settings 4. check for security update |  |  | Failed
| User Management_04 | Verifying Update account information | User can update account information any time | Found as per expectation | Name: "saima" location : "dhaka" sublocation: "kafrul" | 1. Go to Bikroy.com 2. Login to the account 3. Goto account settings 4. fill up-to-date data and click on update |  |  | Passed
| User Management_05 | Verifying Change Password functionality | Users can change their password securely and successfully | Found as per expectation | current passowrd : "12345" new password : "456789" confirm new password : "456789" | 1. Go to Bikroy.com 2. Login to the account 3. Goto account settings 4. Check for change password option 5. Change password with valid credentials |  |  | Passed
| User Management_06 | Verifying Email Verification | Users receive a verification email and can confirm their email address | Found as per expectation | email : "salma@gmail.com" pass: ####123 | 1. Go to Bikroy.com 2. Try to signup with email 3. Check the verification email 4. Click on verification link 5. Check if the links works. |  |  | Passed
| User Management_07 | Verifying Account Deletion | Users are able to delete account | Found as per expectation |  | 1. Go to Bikroy.com 2. Login to the account 3. goto account settings 4. Click on delete account 5. select account deletion reason 6. delete account |  |  | Passed
| User Management_08 | Verifying Account Deactivation | USeres are able to deactivated the account and deactivated accounts cannot log in or access account features | No option for account deactivation |  | 1. Go to Bikroy.com 2. Login to the account 3. goto account settings 4. Check for account deactivation option |  |  | Failed
Blank
Messaging | Messaging_01 | Verifying users can compose and send messages to other users | Users are able to enter text, format messages, and attach files | Found as per expectations | message : "how long you have been using "__ " " | 1. Go to Bikroy.com 2. Login to the account 3. Search for an Item 4. Click on chat 5. Send a message 6. Check the message successfully delivered to the other user. |  |  | Passed
| Messaging_02 | Verifying users receive alerts for new messages | Notifications are delivered promptly and accurately | Found as per expectations |  | 1. Go to Bikroy.com 2. Login to the account 3. Search for an Item 4. Click on chat 5. Send a message 6. Check the message successfully delivered to the other user. 7. Wait for other users response 8. Check if the notification comes promptly |  |  | Passed
| Messaging_03 | Verifying reply to incoming messages | Users are able to compose replies, include attachments if necessary, and send responses successfully | Found as per expectations |  | 1. Go to Bikroy.com 2. Login to the account 3. Search for an Item 4. Click on chat 5. Send a message 6. Wait for Other's users reply 7. Send reply message 8. Check if the message delivered successfully. |  |  | Passed
| Messaging_04 | Verifying message forwarding to other users | Users can select messages, enter recipient information, and forward messages securely | No option for message forwarding to other users |  | 1. Go to Bikroy.com 2. Login to the account 3. Search for an Item 4. Click on chat 5. Send a message 6. Wait for Other's users reply 7. Send reply message 8. Check for message forwading option |  |  | Failed
| Messaging_05 | Verifying deletion functionality to ensure users can delete unwanted messages | Deleted messages are removed from the user's inbox and cannot be recovered | No options for particular message deletion |  | 1. Go to Bikroy.com 2. Login to the account 3. Search for an Item 4. Click on chat 5. Send a message 6. Try to delete a unwanted message |  |  | Failed
| Messaging_06 | Verifying block to abusive users or spam messages | Users are able to block senders that are inappropriate | Found as per expectations |  | 1. Go to Bikroy.com 2. Search for an Item 3. Click on chat 4. Send a message 6. Check If other user send any inappropiate message block user function works. |  |  | Passed
| Messaging_07 | Verifying message searching functionality | Users are able to search for any message in a particular chat | No option to search for any message |  | 1. Go to Bikroy.com 2. Search for an Item 3. Click on chat 4. Search for a particular message |  |  | Failed
Blank
Blank
Payment Gateway Integration | Payment_gateway_01 | Verifying payment process for an Ad | User is able to payment successfully for an Ad | Found as per expectations | account info, user info, details info | 1. Goto Bikroy.com 2. Login to account 3. Click on Post Ad 4. Fill up all necessary steps 5. Click on Post Ad 6. Select payment method 7. fillup with all valid information 8. check if the payment is successful and ad is posted in Bikroy |  |  | Passed
| Payment_gateway_02 | Verifying multiple payment method | User is able to pay through multiple options | Found as per expectations | account info, user info, details info | 1. Goto Bikroy.com 2. Login to account 3. Click on Post Ad 4. Fill up all necessary steps 5. Click on Post Ad 6. Select payment method 7. Check all the methods working perfectly |  |  | Not Executed
| Payment_gateway_03 | Verifying payment with not enough balance | User is not able to Post Ad | Found as per expectations | account info, user info, details info | 1. Goto Bikroy.com 2. Login to account 3. Click on Post Ad 4. Fill up all necessary steps 5. Click on Post Ad 6. Select payment method with insufficient balance7. check if the functions work |  |  | Passed
| Payment_gateway_04 | Verifying succesful Ad after payment | System will show the ad to other user once the payment is complete | Found as per expectations | account info, user info, details info | 1. Goto Bikroy.com 2. Login to account 3. Click on Post Ad 4. Fill up all necessary steps 5. Click on Post Ad 6. Select payment method 7. fillup with all valid information 8. Check if the product is up to other users immediately after the payment is done. |  |  | Passed

## Test Summary Report
TEST CASE SUMMARY
Test Case Report
Project Name | Bikroy
Module Name | Core Functionalities
Feature Name | Registration/SignUp | Searching Items | Browsing | Purchasing Item | User Account Management
| Messaging | Payment Gateway Integration
Test Case Version | 1
Written By | Saima Binta Younus
Executed By | Saima Binta Younus
Reviewed By | XpeedStudio
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total Test Case
Grand Total | 30 | 17 | 1 | 0 | 48
RESULT SUMMAY
Total No. | Status
30 | PASS
17 | FAIL
1 | Not Executed
0 | Out of Scope
RESULT SUMMAY In Pie Chart